## Issue Tracking Template
Issue Tracking Template
ID | Description | Potential Impact | Priority | Date Opened | Date Closed | Issue Owner | Department | Status | Notes
1 | Website loading slowly on ie10 | 5% of visitors may expereince lag | Critical | 2020-04-05 |  | Dale | IT | Open | For whenever Dale has free time
2 | Website crashing at credit card collection screen | Massive loss of revenue | Low | 2020-04-09 |  | Julie | IT | Open | Need to send report to C-suite on this
4 | Serving old format images | poor SEO results | Medium | 2020-03-25 |  | Sarah | SEO | Open | See Google's reccomendartions
5 | Login icons broken on Homepage | Some users unable to login w/ icons | High | 2020-04-03 | 2020-04-09 | Julie | IT | Closed | Completed 4/6/20
6
7
8
9
10
Free Related Templates
Project dashboard template for Excel
Risk tracking template for Excel
Change log template for Excel